## Task&ResoucesAss
Istanbul Metropolitan Municipality-Dept. of Transportation
Şehzadebaşı Cad 25,
34134 Fatih Istanbul, Turkey
Golden Horn Swing Bridge Installation Project
Tender HB-S/2021
Contract Specifications
Project data
WBS: Tasks & Resources Assignments
Phase Id | Element Id | WBS | Resource Initials | Task / Resource Name | Duration | Work | Assignment Units | Cost
|  | 0 |  | 2-5-Tender-CS-TS-0
31-30 50 14 |  | 1 |  | Contract Award Phase
|  | 1.1 |  | Award date (M0.1) | 0 days
|  | 1.2 |  | Contract Bonds effective | 45 days
|  |  | O14.PM | Project Manager |  |  | 100%
|  | 1.3 |  | Notice to proceed (M0.2) | 0 days
31-20 20 14 |  | 2 |  | Final Design Phase
| 21-01 10 20 15 | 2.1 |  | Bored Piles | 60 days
|  |  | O1 | Owner Resources
| 21-01 40 40 | 2.2 |  | Pits and Bases | 25 days
|  |  | O1 | Owner Resources
| 21-06 10 20 70 | 2.3 |  | Towers | 20 days
|  |  | O1 | Owner Resources
| 21-07 20 60 70 | 2.4 |  | Site Bridges
|  | 2.4.1 |  | Approach Viaduct | 90 days
|  |  | O1 | Owner Resources
|  | 2.4.2 |  | Central Cable stayed spans | 150 days
|  |  | O1 | Owner Resources
|  | 2.4.3 |  | FD-Swing Bridge (M1)
|  | 2.4.3.1 |  | Cylinder and Locking Devices
|  |  | O14.PE | Turkish Project Engineer |  | 256 hrs | 50%
|  |  | O14.ME | Turkish Mechanical Engineer |  | 2,048 hrs | 400%
|  | 2.4.3.2 |  | Machinery Room
|  |  | O14.PE | Turkish Project Engineer |  | 340 hrs | 50%
|  |  | O14.ME | Turkish Mechanical Engineer |  | 2,720 hrs | 400%
|  | 2.4.3.3 |  | Swing Bridge Deck
|  |  | O14.PE | Turkish Project Engineer |  | 292 hrs | 50%
|  |  | O14.ME | Turkish Mechanical Engineer |  | 2,336 hrs | 400%
31-40 20 17 |  | 3 |  | Permitting Phase
| 21-07 20 60 70 | 3.1 |  | Site Bridges | 180 days
|  |  | O1 | Owner Resources
|  |  | O14.PE | Turkish Project Engineer |  | 720 hrs | 50%
31-40 20 34 |  | 4 |  | Coordination Phase
| 21-07 20 60 70 | 4.1 |  | Site Bridges | 60 days
|  |  | O14.PE | Turkish Project Engineer |  | 240 hrs | 50%
31-40 20 14 |  | 5 |  | Subcontracting Phase
| 21-07 20 60 70 | 5.1 |  | Site Bridges
|  | 5.1.1 |  | Swing Bridge
|  | 5.1.1.1 |  | Machinery Room
|  | 5.1.1.1.1 |  | RFP
|  |  | O14.PA | Purchasing Agent |  | 40 hrs | 100%
|  | 5.1.1.1.2 |  | BID preparation | 15 days
|  |  | S | S/Contractor
|  | 5.1.1.1.3 |  | BID evaluation
|  |  | O14.PE | Turkish Project Engineer |  | 32 hrs | 100%
|  |  | O14.PA | Purchasing Agent |  | 32 hrs | 100%
|  | 5.1.1.1.4 |  | S/Contract execution
|  |  | O14.PA | Purchasing Agent |  | 16 hrs | 100%
|  |  | S | S/Contractor |  | 8 hrs | 100%
|  | 5.1.1.2 |  | Swing Bridge Deck
|  | 5.1.1.2.1 |  | RFP
|  |  | O14.PA | Purchasing Agent |  | 40 hrs | 100%
|  | 5.1.1.2.2 |  | BID preparation | 15 days
|  |  | S | S/Contractor
|  | 5.1.1.2.3 |  | BID evaluation
|  |  | O14.PE | Turkish Project Engineer |  | 32 hrs | 100%
|  |  | O14.PA | Purchasing Agent |  | 32 hrs | 100%
|  | 5.1.1.2.4 |  | S/Contract execution
|  |  | O14.PA | Purchasing Agent |  | 16 hrs | 100%
|  |  | S | S/Contractor |  | 8 hrs | 100%
31-25 10 21 |  | 6 |  | Fabrication Drawing Preparation Phase
| 21-07 20 60 70 | 6.1 |  | Site Bridges
|  | 6.1.1 |  | Swing Bridge
|  | 6.1.1.1 |  | Cylinder and Locking Devices | 20 days
|  |  | O14.PE | Turkish Project Engineer |  |  | 100%
|  |  | S | Supplier |  |  | 100%
|  | 6.1.1.2 |  | Machinery Room | 15 days
|  |  | O14.PE | Turkish Project Engineer |  |  | 100%
|  |  | S | S/Contractor |  |  | 100%
|  | 6.1.1.3 |  | Swing Bridge Deck | 30 days
|  |  | O14.PE | Turkish Project Engineer |  |  | 100%
|  |  | S | S/Contractor |  |  | 100%
31-40 30 21 |  | 7 |  | Product Purchasing Phase
| 21-07 20 60 70 | 7.1 |  | Site Bridges
|  | 7.1.1 |  | Swing Bridge
|  | 7.1.1.1 |  | Cylinder and Locking Devices
|  | 7.1.1.1.1 |  | RFP
|  |  | O14.PA | Purchasing Agent |  | 40 hrs | 100%
|  | 7.1.1.1.2 |  | BID preparation | 15 days
|  |  | S | Supplier
|  | 7.1.1.1.3 |  | BID evaluation
|  |  | O14.PE | Turkish Project Engineer |  | 32 hrs | 100%
|  |  | O14.PA | Purchasing Agent |  | 32 hrs | 100%
|  | 7.1.1.1.4 |  | Supply Contract execution
|  |  | O14.PA | Purchasing Agent |  | 12 hrs | 100%
|  |  | S | Supplier |  | 12 hrs | 100%
|  | 7.1.1.2 |  | Deck materials | 10 days
|  |  | O14.PA | Purchasing Agent |  | 80 hrs | 100%
|  | 7.1.1.3 |  | Electric & mechanical components | 10 days
|  |  | O14.PA | Purchasing Agent |  | 80 hrs | 100%
31-40 40 14 21 |  | 8 |  | Off-Site Fabrication Phase
| 21-07 20 60 70 | 8.1 |  | Site Bridges
|  | 8.1.1 |  | Swing Bridge
|  | 8.1.1.1 |  | Cylinder and Locking Devices | 280 days
|  |  | S | Supplier
|  |  | O14.MAT | Swing Bridge Materials |  |  |  | 1540200
|  | 8.1.1.2 |  | Deck materials | 60 days
|  |  | S | Supplier
|  | 8.1.1.3 |  | Electric & mechanical components | 60 days
|  |  | S | Supplier
31-40 30 27 |  | 9 |  | Product Delivery Phase
| 21-07 20 60 70 | 9.1 |  | Site Bridges
|  | 9.1.1 |  | PD-Swing Bridge (M2)
|  | 9.1.1.1 |  | Cylinder and Locking Devices | 25 days
|  |  | O14.PA | Purchasing Agent |  |  | 100%
|  |  | O14.F.CH | Ship Freight (Origin China) |  |  | 11 TEU-CN
|  | 9.1.1.2 |  | Deck materials | 5 days
|  |  | O14.PA | Purchasing Agent |  |  | 100%
|  |  | O14.F.TK | Ship Freight (Origin Turkey) |  |  | 32 TEU-TK
|  | 9.1.1.3 |  | Electric & mechanical components | 5 days
|  |  | O14.PA | Purchasing Agent |  |  | 100%
|  |  | O14.F.TK | Ship Freight (Origin Turkey) |  |  | 4 TEU-TK
31-40 40 14 14 |  | 10 |  | Assembly Phase
| 21-07 20 60 70 | 10.1 |  | Site Bridges
|  | 10.1.1 |  | Swing Bridge
|  | 10.1.1.1 |  | Cylinder and Locking Devices | 152 days
|  |  | O14.TW | Team of Turkish Workers (5 Workers each) |  |  | 400%
|  |  | O14.MAT | Swing Bridge Materials |  |  |  | 1206800
|  | 10.1.1.2 |  | Swing Bridge Deck | 88 days
|  |  | O14.TW | Team of Turkish Workers (5 Workers each) |  |  | 400%
|  |  | O14.MAT | Swing Bridge Materials |  |  |  | 5543954
31-40 40 14 11 |  | 11 |  | Erection Phase
| 21-01 10 20 15 | 11.1 |  | Bored Piles | 60 days
|  |  | O1 | Owner Resources
| 21-01 40 40 | 11.2 |  | Pits and Bases | 25 days
|  |  | O1 | Owner Resources
| 21-06 10 20 70 | 11.3 |  | Towers | 20 days
|  |  | O1 | Owner Resources
| 21-07 20 60 70 | 11.4 |  | Site Bridges
|  | 11.4.1 |  | Approach Viaduct | 90 days
|  |  | O1 | Owner Resources
|  | 11.4.2 |  | Central Cable stayed spans | 150 days
|  |  | O1 | Owner Resources
|  | 11.4.3 |  | Swing Bridge
|  | 11.4.3.1 |  | Cylinder and Locking Devices | 50 days
|  |  | O14.TW | Team of Turkish Workers (5 Workers each) |  |  | 400%
|  | 11.4.3.2 |  | Machinery Room | 85 days
|  |  | O14.TW | Team of Turkish Workers (5 Workers each) |  |  | 400%
|  |  | O14.MAT | Swing Bridge Materials |  |  |  | 3095000
|  | 11.4.3.3 |  | Swing Bridge Deck | 30 days
|  |  | O14.TW | Team of Turkish Workers (5 Workers each) |  |  | 400%
31-40 50 11 |  | 12 |  | Commissioning Start-Up Phase
| 21-07 20 60 70 | 12.1 |  | CS-Site Bridges (M3)
|  | 12.1.1 |  | Swing Bridge | 32 days
|  |  | O14.PE | Turkish Project Engineer |  |  | 100%
|  |  | O14.ME | Turkish Mechanical Engineer |  |  | 400%
|  |  | O14.TW | Team of Turkish Workers (5 Workers each) |  |  | 400%

## ResBS data
Istanbul Metropolitan Municipality-Dept. of Transportation
Şehzadebaşı Cad 25,
34134 Fatih Istanbul, Turkey
Golden Horn Swing Bridge Installation Project
Tender HB-S/2021
Contract Specifications
Project data
OBS / ResBS
Group | Resource Name | Type | Material Label | Initials | Max. Units | Std. Rate
Obs.1 | Owner Resources | Work |  | O1
Obs.2 | Authority | Work |  | A
Obs.14 | Project Manager | Work |  | O14.PM | 100% | €180.00/hr
Obs.14 | Turkish Project Engineer | Work |  | O14.PE | 100% | €60.00/hr
Obs.14 | Turkish Mechanical Engineer | Work |  | O14.ME | 400% | €43.00/hr
Obs.14 | Purchasing Agent | Work |  | O14.PA | 100% | €80.00/hr
Obs.14 | Supplier | Work |  | S
Obs.14 | S/Contractor | Work |  | S
Obs.14 | Team of Turkish Workers (5 Workers each) | Work |  | O14.TW | 800% | €150.00/hr
Obs.14 | Swing Bridge Materials | Cost |  | O14.MAT
Obs.14 | Ship Freight (Origin China) | Material | TEU-CN | O14.F.CH |  | 1440
Obs.14 | Ship Freight (Origin Turkey) | Material | TEU-TK | O14.F.TK |  | 212