## CostTimeAnalysis
|  |  | Cost |  |  |  | Time
Code | Description | UoM | Unit Cost | Q.ty | Cost | S/total | Work | Units | Duration
E.02.030.010.f | Bored pile - Diameter 1200 mm | m | 162.58 | [5 empty] | 0.36 | hr/m
Bored pile, rotary drilling rig, through soil of any nature and compaction for pile length up to 25m.
Includes:
Crossing of rock or compact clay lenses up to 30 cm thick
Tremie pipe, Cast in site Concrete, class C25/30
Equipment mobilization and demobilization
Bottom bulb formation
Pile top preparation
Pile tests
Drilling and extraction of soil
Excludes:
Steel reinforcement
Pile wall support
Transport of excavated soil
Measurement
Actual tip to toe pile length according to design neat lines
A | Direct Costs |  |  |  |  | 162.58
A1 | Labor |  |  |  |  | 19.8
| Common Labor | hr | 25 | 0.36 | 9 |  | 0.36 | 1
| Specialized labor | hr | 30 | 0.36 | 10.8 |  | 0.36 | 1
A2 | Materials |  |  |  |  | 97.96
| Ready mix Concrete XC1-XC2, S4, 32mm, C25/30 | m3 | 79 | 1.24 | 97.96
A3 | Rentals and fees |  |  |  |  | 44.82
| Front loader, 90HP, bucket 1,2m3 | hr | 48 | 0.02 | 0.96 |  | 0.02 | 0.06
| Tipping truck, 15m3 | hr | 80 | 0.02 | 1.6 |  | 0.02 | 0.06
| Air compressor 5000 l/min | hr | 24 | 0.06 | 1.44 |  | 0.06 | 0.17
| Compressed air bootom hammer | hr | 31 | 0.06 | 1.86 |  | 0.06 | 0.17
| Concrete pump | hr | 52 | 0.08 | 4.16 |  | 0.08 | 0.22
| Rotary rig, large diameter piling, 280HP | hr | 145 | 0.24 | 34.8 |  | 0.36 | 1

## Schedule
34.4
hrs/m
|  |  |  | Duration | 8 | UoM | Qty | req.d | base | no. rigs
|  |  |  | [days] | [hrs]
31-40 40 14 11 |  | Erection phase
| 21-01 10 20 15 | Bored piles |  | 60 | 480 | m | 3600 | 0.13333 | 0.36 | 2.7
|  |  | West viaduct |  |  | m | 2400
|  |  | Piers | 6
|  |  | Pile / Pier | 10
|  |  | Avg. length | 40
|  |  | East viaduct |  |  | m | 1200
|  |  | Piers | 6
|  |  | Pile / Pier | 10
|  |  | Avg. length | 20

## Bored Piles details
Optimized solution
[9 empty] | 2 | rigs per pier
21-01 10 20 15 | Bored piles |  |  | UoM | Q.ty | hrs/UoM | Duration | 8 | UoM | Q.ty | hrs/UoM | Duration | 8
[7 empty] | hrs | days |  |  |  | hrs | days
|  | West Viaduct |  | m | 2400 | 0.36 | 864 | 108 |  |  | 0.03 | 72 | 9
|  |  | Piers | [5 empty] | 6
|  |  | Resource name | Units |  |  |  |  | Units
|  |  | Common Labor | 1 |  |  |  |  | 12
|  |  | Specialized labor | 1 |  |  |  |  | 12
|  |  | Front loader, 90HP, bucket 1,2m3 | 0.06 |  |  |  |  | 0.72
|  |  | Tipping truck, 15m3 | 0.06 |  |  |  |  | 0.72
|  |  | Air compressor 5000 l/min | 0.17 |  |  |  |  | 2.04
|  |  | Compressed air bootom hammer | 0.17 |  |  |  |  | 2.04
|  |  | Concrete pump | 0.22 |  |  |  |  | 2.64
|  |  | Rotary rig, large diameter piling, 280HP | 1
|  | East Viaduct |  | m | 1200 | 0.36 | 432 | 54 |  |  | 0.03 | 36 | 4.5
|  |  | Piers | [5 empty] | 6
|  |  | Resource name | Units |  |  |  |  | Units
|  |  | Common Labor | 1 |  |  |  |  | 12
|  |  | Specialized labor | 1 |  |  |  |  | 12
|  |  | Front loader, 90HP, bucket 1,2m3 | 0.06 |  |  |  |  | 0.72
|  |  | Tipping truck, 15m3 | 0.06 |  |  |  |  | 0.72
|  |  | Air compressor 5000 l/min | 0.17 |  |  |  |  | 2.04
|  |  | Compressed air bootom hammer | 0.17 |  |  |  |  | 2.04
|  |  | Concrete pump | 0.22 |  |  |  |  | 2.64
|  |  | Rotary rig, large diameter piling, 280HP | 1 |  |  |  |  | 12