## WBS
Istanbul Metropolitan Municipality-Dept. of Transportation
Şehzadebaşı Cad 25,
34134 Fatih Istanbul, Turkey
Golden Horn Swing Bridge Installation Project
Tender HB-S/2021
Contract Specifications
Project data |  | 31-30 50 14 | Contract Award Phase
Work Breakdown Structure
Resources
Phase |  | Element |  | Section | Task | OBS |  | Start | DURATION | Name | WORK | UNITS | Name | WORK | UNITS | Name | WORK | UNITS | Material Cost
31-30 50 14 | Contract Award Phase
Award date
31-20 20 14 | Final Design Phase
|  | 21-01 10 20 15 | Bored Piles | [5 empty] | 15
|  |  |  | Approach Viaduct |  | Obs.12 | Piling Contractor
|  |  |  | Swing Bridge |  | Obs.12 | Piling Contractor
|  |  |  | Central Cable stayed spans |  | Obs.12 | Piling Contractor
|  | 21-01 40 40 | Pits and Bases | [5 empty] | 10
|  |  |  | Swing Bridge |  | Obs.13 | Bridge Contractor
|  | 21-06 10 20 70 | Towers | [5 empty] | 20
|  |  |  | Approach Viaduct |  | Obs.13 | Bridge Contractor
|  |  |  | Central Cable stayed spans |  | Obs.13 | Bridge Contractor
|  | 21-07 20 60 70 | Site Bridges
|  |  |  | Approach Viaduct |  | Obs.13 | Bridge Contractor |  | 30
|  |  |  | Central Cable stayed spans |  | Obs.13 | Bridge Contractor |  | 60
Swing Bridge
[5 empty] | Cylinder and Locking Devices | Obs.1401 | SB-Pr. Engineer |  | 64 | Turkish Mechanical Engineer |  | 4 | Turkish Project Engineer |  | 0.5
[5 empty] | Machinery Room | Obs.1401 | SB-Pr. Engineer |  | 85 | Turkish Mechanical Engineer |  | 4 | Turkish Project Engineer |  | 0.5
[5 empty] | Swing Bridge Deck | Obs.1401 | SB-Pr. Engineer |  | 73 | Turkish Mechanical Engineer |  | 4 | Turkish Project Engineer |  | 0.5
31-40 20 17 | Permitting Phase
|  | 21-07 20 60 70 | Site Bridges |  |  | Obs.2 | Istanbul Ports Authority |  | 90
31-40 20 34 | Coordination Phase
|  | 21-07 20 60 70 | Site Bridges |  |  | Obs.11 | O.Engineer |  | 30
31-40 20 14 | Subcontracting Phase
|  | 21-07 20 60 70 | Site Bridges
Swing Bridge
[5 empty] | Machinery Room | Obs.1405 | SB-Procurement |  |  | Purchasing Agent | 88 | 2 | Turkish Project Engineer | 16 | 2
[5 empty] | Swing Bridge Deck | Obs.1405 | SB-Procurement |  |  | Purchasing Agent | 88 | 2 | Turkish Project Engineer | 16 | 2
31-25 10 21 | Fabrication Drawing Preparation Phase
|  | 21-07 20 60 70 | Site Bridges
Swing Bridge
[5 empty] | Cylinder and Locking Devices | Obs.140201 | SB-CL-Engineering |  | 20 | Supplier |  |  | Turkish Project Engineer |  | 0.5
[5 empty] | Machinery Room | Obs.140301 | SB-MR-Engineering |  | 15 | S/Contractor |  |  | Turkish Project Engineer |  | 0.5
[5 empty] | Swing Bridge Deck | Obs.140401 | SB-BD-Engineering |  | 30 | S/Contractor |  |  | Turkish Project Engineer |  | 0.5
31-40 30 21 | Product Purchasing Phase
|  | 21-07 20 60 70 | Site Bridges
Swing Bridge
[5 empty] | Cylinder and Locking Devices | Obs.1405 | SB-Procurement |  | 120 | Purchasing Agent |  | 2 | Turkish Project Engineer | 16 | 2
[5 empty] | Deck materials | Obs.1405 | SB-Procurement |  | 30 | Purchasing Agent |  | 2 | Turkish Project Engineer | 16 | 2
[5 empty] | Electric & mechanical components | Obs.1405 | SB-Procurement |  | 60 | Purchasing Agent |  | 2 | Turkish Project Engineer | 16 | 2
31-40 40 14 21 | Off-Site Fabrication Phase
|  | 21-07 20 60 70 | Site Bridges
Swing Bridge
[5 empty] | Cylinder and Locking Devices | Obs.140202 | SB-CL-Factory |  | 280 | Supplier | [8 empty] | 1540200
31-40 30 27 | Product Delivery Phase
|  | 21-07 20 60 70 | Site Bridges
Swing Bridge
[5 empty] | Cylinder and Locking Devices | Obs.140203 | SB-CL-Site |  | See Transportation Sheet
[5 empty] | Deck materials | Obs.1405 | SB-Procurement
[5 empty] | Electric & mechanical components | Obs.1405 | SB-Procurement
31-40 40 14 14 | Assembly Phase
|  | 21-07 20 60 70 | Site Bridges
Swing Bridge
[5 empty] | Cylinder and Locking Devices | Obs.140203 | SB-CL-Site |  | 152 | Team of Turkish Workers (5 Workers each) |  | 4 | [6 empty] | 1026800
[5 empty] | Swing Bridge Deck | Obs.140402 | SB-BD-Site |  | 58 | Team of Turkish Workers (5 Workers each) |  | 4 | [6 empty] | 5543954
31-40 40 14 11 | Erection Phase
|  | 21-07 20 60 70 | Site Bridges
Swing Bridge
[5 empty] | Cylinder and Locking Devices | Obs.140203 | SB-CL-Site |  | 75 | Team of Turkish Workers (5 Workers each) |  | 4
[5 empty] | Machinery Room | Obs.140302 | SB-MR-Site |  | 25 | Team of Turkish Workers (5 Workers each) |  | 4 | [6 empty] | 3095000
[5 empty] | Swing Bridge Deck | Obs.140402 | SB-BD-Site |  | 88 | Team of Turkish Workers (5 Workers each) |  | 4
31-40 50 11 | Commissioning Start-Up Phase
|  | 21-07 20 60 70 | Site Bridges
Swing Bridge
[6 empty] | Obs.1401 | SB-Pr. Engineer |  | 32 | Turkish Mechanical Engineer |  | 4 | Team of Turkish Workers (5 Workers each) |  | 8 | Turkish Project Engineer |  | 1 | 225000

## OBS
ID
Obs.1 | Owner
Obs.11 | O.Engineer
Obs.12 | Piling Contractor
Obs.13 | Bridge Contractor
Obs.14 | Swing Bridge Contractor
Obs.1401 | SB-Pr. Engineer
Obs.1402 | SB-Supplier: Cylinder and Locking Devices
Obs.140201 | SB-CL-Engineering
Obs.140202 | SB-CL-Factory
Obs.140203 | SB-CL-Site
Obs.1403 | SB-S/Contract: Machinery Room
Obs.140301 | SB-MR-Engineering
Obs.140302 | SB-MR-Site
Obs.1404 | SB-S/Contract: Swing Bridge Deck
Obs.140401 | SB-BD-Engineering
Obs.140402 | SB-BD-Site
Obs.1405 | SB-Procurement
Obs.2 | Istanbul Ports Authority

## ResBS
Human Resources | Unit cost/hour | Currency | max available units | Max available units when crashing | Crashing Conditions
Team of Italian Workers (5 Workers each) | 400 | € | 8 | 10 | Due to the lack of time to conduct proper selection and training you are forced to employ very high skilled workers. Each additional unit will require double the standard rate for the same type of unit. Furthermore, due to space constraints, if you decide to increase the number of units you have to rent a new facilities which will add an additional 1000€/day of OH costs
Team of Turkish Workers (5 Workers each) | 150 | € | 8 | 10
Italian Mechanical Engineer | 85 | € | 4 | 6
Italian Project Engineer | 120 | € | 1 | 1
Turkish Mechanical Engineer | 42.5 | € | 4 | 6
Turkish Project Engineer | 60 | € | 1 | 1
Purchasing Agent | 80 | € | 2 | 2

## Transportation
| TEU/Unit | Origin | Duration (d) | Duration (d) - MITIGATION
Lift and Turn Cylinder | 6 | China | 25 | 10
Locking Devices | 5 | Turkey | 5
Machinery Room | 4 | Turkey | 5
Steel Material | 32 | Turkey | 5
€/TEU
Ship | 1440