## 1
BCWS | sem 1, 2013 | sem 2, 2013 | sem 1, 2014 | sem 2, 2014 | sem 1, 2015 | sem 2, 2015 | CI | SI($) | EAC (per task) | AC
Component identification | 200000 | 90000
Preclinical test |  | 50000 | 200000
Clinical program |  |  |  | 260000 | 200000
Launch | [5 empty] | 100000
Marketing and legal support |  | 10000 | 30000 | 50000 | 100000
Prj mng support | 30000 | 30000 | 30000 | 30000 | 30000 | 30000
Corporate overhead | 100000 | 100000 | 100000 | 100000 | 100000 | 100000
ACWP | sem 1, 2013 | sem 2, 2013 | sem 1, 2014 | sem 2, 2014 | sem 1, 2015 | sem 2, 2015
Component identification | 190000 | 130000
Preclinical test |  | 60000 | 220000 | 40000
Clinical program |  |  |  | 170000
Launch
Marketing and legal support |  | 10000 | 30000 | 50000
Prj mng support | 30000 | 30000 | 30000 | 30000
Corporate overhead | 100000 | 100000 | 100000 | 100000
BCWP | sem 1, 2013 | sem 2, 2013 | sem 1, 2014 | sem 2, 2014 | sem 1, 2015 | sem 2, 2015
Component identification | 180000 | 110000 |  |  |  |  | 0.90625 | 1 | 320000
Preclinical test |  | 40000 | 180000 | 30000 |  |  | 0.78125 | 1 | 320000
Clinical program |  |  |  | 160000 |  |  | 0.94118 | 0.61538 | 794218.75 | 3.25
Launch | [8 empty] | 100000
Marketing and legal support |  | 10000 | 30000 | 50000 |  |  | 1 | 1 | 190000
Prj mng support | 30000 | 30000 | 30000 | 30000 |  |  | 1 | 1 | 150000
Corporate overhead | 100000 | 100000 | 100000 | 100000 |  |  | 1 | 1 | 600000
All tasks | sem 1, 2013 | sem 2, 2013 | sem 1, 2014 | sem 2, 2014 | sem 1, 2015 | sem 2, 2015
| 1 | 2 | 3 | 4 | 5 | 6
BCWS | 330000 | 280000 | 360000 | 440000 | 430000 | 230000
ACWP | 320000 | 330000 | 380000 | 390000
BCWP | 310000 | 290000 | 340000 | 370000
All tasks - Cumulative
BCWS | 330000 | 610000 | 970000 | 1410000 | 1840000 | 2070000
ACWP | 320000 | 650000 | 1030000 | 1420000
BCWP | 310000 | 600000 | 940000 | 1310000
CI | 0.96875 | 0.92308 | 0.91262 | 0.92254
CRITICAL PATH
BCWS | 200000 | 340000 | 540000 | 800000 | 1000000 | 1100000
BCWP | 180000 | 330000 | 510000 | 700000
SI($) | 0.9 | 0.97059 | 0.94444 | 0.875
SI(t) |  | 0.96429 | 0.95 | 0.90385
Cost of acceleration (CR)
CEAC - Synthetic integrated index (average behavior)
2289213.9029 | EAC=BAC/(CI*SI(t))
CEAC - Line by line
2474218.75
Cost of delay using average SI(t) |  |  |  |  | Cost of delay using line by line approach
AC | 6.6383 |  |  |  | AC | 7.25
EAC |  |  | 2243816.7939 |  |  |  |  | 2243816.7939
Loss of sales | 0.6383 | 300000 | 191489.3617 |  |  | 1.25 | 300000 | 375000
|  |  | 2435306.1556 |  |  |  |  | 2618816.7939
In any case, acceleration is less expensive than cost of delay
better to consider straight linear impact of O/H cost

## 2 (hidden)
TASK | optimistic duration [weeks] | most likely duration [weeks] | pessimistic duration [weeks] | PREDECESSOR | m | d | V
Basic design | 4 | 8 | 12 |  | 8 | 1.3333 | 1.7778
Detailed design | 9 | 12 | 18 | basic design | 12.5 | 1.5 | 2.25
Procurement | 24 | 26 | 40 | basic design | 28 | 2.6667 | 7.1111
Civil works erection | 12 | 14 | 22 | detailed design | 15 | 1.6667 | 2.7778
Assembly of production line | 12 | 16 | 20 | procurement; civil works erection | 16 | 1.3333 | 1.7778
Testing | 3 | 4 | 8 | assembly of production line | 4.5 | 0.83333 | 0.69444
| z | p
bd-proc-ass-test | 0.44502 | 67.36% |  |  | 56.5 | 3.3706 | 11.3611
bd-dd-cw-ass-test | 0.3 | 61.79% |  |  | 56 | 6.6667 | 9.2778
p1*p2 |  | 41.62%

## 4
Task (AON) | Optimistic duration [weeks] | Most likely | Pessimistic duration | e | d | V | z | p
1-2 | 5 | 11 | 11 | 10 | 1 | 1
1-3 | 10 | 10 | 10 | 10 | 0 | 0
1-4 | 2 | 5 | 8 | 5 | 1 | 1
2-6 | 1 | 7 | 13 | 7 | 2 | 4
3-6 | 4 | 4 | 10 | 5 | 1 | 1
3-7 | 4 | 7 | 16 | 8 | 2 | 4
3-5 | 2 | 2 | 14 | 4 | 2 | 4
4-5 | 0 | 6 | 12 | 6 | 2 | 4
5-7 | 2 | 8 | 14 | 8 | 2 | 4
6-7 | 1 | 4 | 7 | 4 | 1 | 1
[7 empty] | 20 | less than | 23 | more than | less than
1-2-6-7 | P1 |  |  | 21 | 2.4495 | 6 | -0.40825 | 35% | 0.8165 | 21% | 79%
1-3-6-7 | P2 |  |  | 19 | 1.4142 | 2 | 0.70711 | 76% | 2.8284 | 1% | 99%
1-3-7 | P3 |  |  | 18 | 2 | 4 | 1 | 84% | 2.5 | 1% | 99%
1-3-5-7 | P4 |  |  | 22 | 2.8284 | 8 | -0.70711 | 25% | 0.35355 | 36% | 64%
1-4-5-7 | P5 |  |  | 19 | 3 | 9 | 0.33333 | 63% | 1.3333 | 9% | 91%
[7 empty] | P1*P2*P3*P4*P5 | 3.519% |  | 54.91% | 50.05%
CRITICAL PATH ONLY
decision tree
status | outcome | likelihood | utility
S1 | 25 | 25% | 1
S2 | 0 | 39% | 1
S3 | -5 | 36% | 1
average | 4.45 | >0 | positive, bid
MERGE NODE BIAS
decision tree
status | outcome | likelihood | utility
S1 | 25 | 3.519% | 1
S2 | 0 | 41.57% | 1
S3 | -5 | 54.91% | 1
average | -1.8655 | <0 | negative, no bid