## 1
decision
|  |  | duration | cost | ave time | average cost
no staff | 30% | risk | 9 | 80000 | 6.9 | 59000
| 70% | no risk | 6 | 50000
extra staff | 10% | risk | 7 | 68000 | 6.1 | 60800
| 90% | no risk | 6 | 60000
pessimistic rule: extra staff
if o/h less than 1,800 then better to add extra staff
pareto notion

## 2
Task | Duration | Monthly budget cost (k€/month) | BAC | WP | WP | WP | WP | WP | WS | BCWP | BCWS | ACWP
| (month) |  |  | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 5
[8 empty] | (time now) | (time now)
A | 2 | 15 | 30 | 60% | 90% | 100% | 100% | 100% | 100% | 30 | 30
B | 1 | 20 | 20 |  |  | 10% | 100% | 100% | 100% | 20 | 20
C | 4 | 20 | 80 |  |  | 20% | 35% | 50% | 75% | 40 | 60
D | 3 | 30 | 90 |  |  |  | 10% | 20% | 66.67% | 18 | 60
E | 2 | 10 | BAC: 20; WS: 0%; BCWP: 0; BCWS: 0
TOTAL |  |  | BAC: 240; BCWP: 108; BCWS: 170; ACWP: 110
ACWP | 110
Fixed fee | 120
O/H cost | 15 | per month
CI | 0.98182 |  | WP: 108/110
SI($) | 0.61818 | A-B-D-E | BAC: CRITICAL PATH AT TIME NOW; WP: 68/110
SI($) | 0.77778 | A-C-E | WP: relative profit
Revise approach:
| TEAC | 11.0924 | BAC: months
| CEAC | 244.4444
| price | 530.831 | bar: BAC
| profit=fixed fee | 120 | WP: 22.61%; WP: BETTER NOT TO CRASH TO MAXIMIZE RELATIVE PROFIT %ROC (AS PROFIT IS THE SAME IN BOTH SCENARIOS)
CR crashing: |  |  | WP: DISCUSSION OF RESULTS IS APPRECIATED
| TEAC | 8 | BAC: months
| CEAC | 338.9356 | bar: BAC
| price | 578.9356 | bar: BAC
| profit=fixed fee | 120 | WP: 20.73%
SI(t) | 0.72121 | A-B-D-E
|  |  |  | 18 | 27 | 30 | 30 | 30
|  |  |  | 0 | 0 | 2 | 20 | 20
|  |  |  | 0 | 0 | 0 | 9 | 18
BCWP |  |  | WP: 18; WP: 27; WP: 32; WP: 59; WP: 68
|  |  |  | 15 | 30 | 30 | 30 | 30
[6 empty] | 20 | 20 | 20
[7 empty] | 29.7 | 29.7
BCWS |  |  | WP: 15; WP: 30; WP: 50; WP: 79.7; WP: 79.7
ES | 3.6061