## 1
no mitigation |  | prob | d | direct cost | o/h | penalty | overrun share | fixed fee | price | profit
| risk | 40% | 19 | 6000 | 1900 | -150 | -150 | 400 | 8000 | 100 | 280
| no risk | 60% | 16 | 6000 | 1600 | 0 | 0 | 400 | 8000 | 400 |  | best decision
mitigation
| risk | 40% | 16 | 6800 | 1600 | 0 | -400 | 400 | 8400 | 0 | 90
| no risk | 60% | 13 | 6800 | 1300 | 0 | -250 | 400 | 8250 | 150
| Task | Immediate Predecessor | Duration [months]
| A. Basic design and building permits | - | 2
| B. Detailed design | A | 2
| C. Procurement of precast building | A | 6
| D. Procurement of production equipment | B | 3
| E. Site preparation and foundations | A | 2
| F. Precast building erection | E, C | 4
| G. Internal utilities | F | 1
| H. Installation of production line | B, F, G | 2
| I. Test | H | 1

## 2
Task | BAC | BCWS | BCWP | ACWP | CI | SI
A. Basic design and building permits | 200 | 200 | 200 | 220 | 0.90909 | 1
B. Detailed design | 300 | 280 | 300 | 200 | 1.5 | 1.0714
C. Procurement of precast building | 1400 | 1400 | 1450 | 1600 | 0.90625 | 1.0357
D. Procurement of production equipment | 1600 | 1000 | 1200 | 800 | 1.5 | 1.2
E. Site preparation and foundations | 300 | 280 | 300 | 250 | 1.2 | 1.0714
F. Precast building erection | 700 | 700 | 500 | 600 | 0.83333 | 0.71429
G. Internal utilities | 1000
H. Installation of production line | 400
I. Test | 100
TOTAL | 6000 | 3860 | 3950 | 3670 | 1.0763 | 1.0233
|  | 2300 | 2150 |  |  | 0.93478 | critical path
9 months into the project
| AC | EAC (DIRECT) | O/H | FEE | SHARE | TIME PENALTY | PRICE | PROFIT | profit/price | profit/cost
Option 1 : revise | 17.1163 | 5574.6835 | 1711.6279 | 400 | 156.8443 | -55.814 | 7787.3418 | 501.0303 | 6.434% | 6.876%
Option 2: crash | 16 | 5963.615 | 1600 | 400 | 18.1925 | 0 | 7981.8075 | 418.1925 | 5.239% | 5.529%

## 3
Ex. 3
Determine the approximate debt leverage required to finance a 15,000,000€ BOT capital project. The project is supposed to be operated over 24 years, with 1,000,000€ annual expected pre-tax cash flow before repayment of debt to the bank.
Assume that cost of equity is 10% and cost of debt 5%. Fell free to make other reasonable financial assumptions, if needed.
6
Capex | 15000000 |  |  |  | 1 | Lay out given data | [5 empty] | 1
Ce | 10% |  |  |  | 2 | Assume
Cd | 5% |  |  |  |  | a | DSCR | ie Bankability |  |  | 1.5 | 0.5
CF pretax | 1000000 |  |  |  |  | b | Loan repayment period |  |  |  | 16 | 0.5
[6 empty] | c | Loan amortization |  |  |  | straightline | 0.5
Hp: |  |  |  |  | 3 | Pretax calculation
DSCR pre-tax target | 1.5 | (any value from 1.4 to 2.0 is fine) |  |  |  | a | Calculate Debt based on rate formula (worst case) |  |  |  | 5925925.9259 | 2
Loan repayment period | 16 | typically debt repayment is over 2/3 of life of concession |  |  |  | b | Calculate Debt to Equity |  |  |  | 0.65306 | 0.5
Tax rate | 0.25 |  |  |  | 4 | Post tax calculation | [5 empty] | 1
Tax shield on interest exp | 1 |  |  |  |  | a | Assume Tax rate |  |  |  | 25%
[6 empty] | b | Assume Tax shield on interest |  |  |  | 100%
[6 empty] | c | Calculate CF post tax |  |  |  | 824074.0741
[6 empty] | d | Calculate post tax DSCR |  |  |  | 1.2361
debt | 5556163.9468 | unknown variable to be determined |  |  |  | e | Evaluate post tax DSCR |  | > | 1.2 | ok
Pretax calculation: | =CF/(principal+interest) | worst-case year = year 1 if principal payment constant |  |  |  | f | Calculate WACC |  |  |  | 7.531%
principal | 347260.2467
interest | 277808.1973 | =outstanding debt*Cd
payment | 625068.444
|  |  |  | Investment | 15000000 | D/E | 0.65306
DSCR = | 1.5998 | > | 1.5 | Debt | 5925925.9259
|  |  |  | Equity | 9074074.0741
Post tax calculation can also be provided, but first tax rate mus be assumed and then tax shield must be computed.
Debt | 4800000
Equity | 10200000
D/E | 0.47059

## 3 pdm
Ex. 3
Determine the approximate debt leverage required to finance a 15,000,000€ BOT capital project. The project is supposed to be operated over 24 years, with 1,000,000€ annual expected pre-tax cash flow before repayment of debt to the bank.
Assume that cost of equity is 10% and cost of debt 5%. Fell free to make other reasonable financial assumptions, if needed.
[5 empty] | SCORE | 6
1 | Lay out given data |  |  |  | 1
|  | Capex |  | 15000000
|  | Ce |  | 10%
|  | Cd | cd | 5%
|  | CF pretax | cfg | 1000000
|  | Operation | ni | 24
2 | Assume
| a | DSCR | ie Bankability | 1.5 | 0.5
| b | Loan repayment period | nr | 16 | 0.5
| c | Loan amortization |  | straightline | 0.5
3 | Pretax calculation
| a | Calculate Debt based on rate formula (worst case) |  | 5925925.9259 | 2
D=cfg/DSCRg/(1/nr+cd)
| b | Calculate Debt to Equity |  | 0.65306 | 0.5
Interest=D/nr+D*Cd
4a | Post tax calculation |  |  |  | 1
| a | Assume Tax rate |  | 25%
| b | Calculate Tax shield |  | 100%
|  | EBITDA | =CF | 1000000
|  | Depreciation = Capex / ni |  | 625000
|  | EBIT |  | 375000
|  | Cost of debt=D/nr+D*Cd |  | 666666.6667
|  | Pre Tax Profit |  | -291666.6667
|  | Tax base |  | 0
|  | Tax |  | 0
|  | Net CF |  | 1000000
| c | Calculate post tax DSCR |  | 1.5
| d | Evaluate post tax DSCR >= | 1.2 | ok
4b
| e | Calculate WACC |  | 7.531%
| f | Calculate NPV @WACC |  | -3221041.1909
VAN= R*(1+i)*[1-(1+i)^(-n)]/I - Capex
| g | Evaluate investment |  | KO