## 3
| Task | Predecessor | Normal duration weeks | Normal cost | D accelerat max | accel /w | OH/w | 30
A | User needs and specs |  | 8 | 300 |  |  | penalty/w | 120
B | Sw dev | A | 10 | 500 | 8 | 20
C | Hw procurement | A | 8 | 300
D | System setup | B, C | 6 | 200 | 2 | 100
E | Pre-test | D | 4 | 100
F | Integration w ERP | E, H | 10 | 600 | 6 | 50
G | Final test | F | 4 | 100
H | ERP dev |  | 26
Best case - no risk |  |  |  |  | 42
| duration | direct | oh | total cost | conting=penalty | price
0) normal | 42 | 2100 | 1260 | 3360 | 0 | 3696
1 acc B | 40 | 2140 | 1200 | 3340 | 0 | 3674
2 acc f | 38 | 2400 | 1140 | 3540 | 0 | 3894
Worst case
| durata | diretti | indiretti | costi totali |  | price
0) normal | 46 | 2100 | 1380 | 3480 | 480 | 4356
1 acc B | 44 | 2140 | 1320 | 3460 | 240 | 4070
2 acc f | 42 | 2400 | 1260 | 3660 | 0 | 4026
EVM case |  | 50% | dur task D | 10 |  | average | 8
| durata | diretti | indiretti | costi totali |  | price
0) normal | 44 | 2100 | 1320 | 3420 | 240 | 4026
1 acc B | 42 | 2140 | 1260 | 3400 | 0 | 3740 | right solution
2 acc f | 40 | 2400 | 1200 | 3600 | 0 | 3960
Average price
no risk | 50% |  |  |  |  | 3674 | 3850
yes risk | 50% |  |  |  |  | 4026

## 4
| Task | Duration | status | WS | WP | BAC | BCWS | ACWP | BCWP | SI | TEAC REVISE | TEAC ACCEL | CI
A | User needs and specs | 8 | completed | 100% | 100% | 300 | 300 | 330 | 300 | 1 | 8
B | Sw dev | 8 | in progress | 33% | 50% | 520 | 171.6 | 260 | 260 | 1.5152 | 5.28
C | Hw procurement | 8 | in progress | 50% | 40% | 300 | 150 | 70 | 100 | 0.66667 | 12
D | System setup | 6 | to do | 0% | 0% | 200 | 0 | 0 | 0 |  | 6 | 2
E | Pre-test | 4 | to do | 0% | 0% | 100 | 0 | 0 | 0 |  | 4
F | Integration w ERP | 10 | to do | 0% | 0% | 600 | 0 | 0 | 0 |  | 10 | 6
G | Final test | 4 | to do |  |  | 100 | 0 | 0 | 0 |  | 4
| Date ERP available | 29 |  |  |  | 2120 |  | 660 | 660 |  | 29 |  | 1
| TEAC end of pretest | [9 empty] | 30
| total duration estimate | [9 empty] | 44
SCENARIO 1 REVISE we are causing delay, no correction is taken and we pay all penalty
TEAC |  |  | 44
PREZZO |  |  | 3740
COSTI |  |  | 3700
| CEAC |  | 2140
| indiretti | 30 | 1320
| penali | 120 | 240
PROFITTO |  |  | 40
SCENARIO 2 we are causing delay. So we acceleratefuture activities as to finish on time
TEAC |  |  | 42
PREZZO |  |  | 3740
COSTI |  |  | 3500
| CEAC |  | 2240
| indiretti | 30 | 1260
| penali | 120 | 0
PROFITTO |  |  | 240 | BEST
SCENARIO 3 we accelerate system setup so client is causing delay and we do not need to pay penalties
TEAC |  |  | 43
PREZZO |  |  | 3740
COSTI |  |  | 3630
| CEAC |  | 2340 | IT IS TOO EXPENSIVE TO CRASH system setup
| indiretti | 30 | 1290
| penali | 120 | 0
PROFITTO |  |  | 110