## 1
Task | Original Duration [days] | Original Budgeted Cost [€] | WS | WP | BCWP | BCWS | ACWP | CI | SI
A | 13 | 12000 | 100% | 100% | 12000 | 12000 | 15000 | 0.8 | 1
B | 8 | 16000 | 100% | 100% | 16000 | 16000 | 18000 | 0.88889 | 1
C | 16 | 22000 | 70% | 56% | 12320 | 15400 | 14747.5 | 0.8354 | 0.8
D | 12 | 17000 | 54% | 0% | 0 | 9180 |  |  | 0
E | 4 | 22000 | 0% | 0% | 0 | 0
F | 14 | 23000 | 0% | 0% | 0 | 0
G | 14 | 21000 | 0% | 0% | 0 | 0
H | 3 | 19000 | 0% | 0% | 0 | 0
| 42 | 152000 | [5 empty] | 0.84444
oh | 1000
OPTION 1 - DO NOTHING
| teac |  | CEAC | oh | fixed fee | target cost | price | profit | ROC
path ADGH | 49 | critical | 180000.496 | 49000 | 100000 | 152000 | 266000.248 | 36999.752 | 16.16% | second-best | 0.875
path BCEF | 46
OPTION 2 - CRASH CRITICAL TO 46 ACCELERATE D
Both paths critical | 46 |  | 183553.1374 | 46000 | 100000 | 152000 | 267776.5687 | 38223.4313 | 16.65% | BEST
tough little marginal advantag
OPTION 3 - CRASH BOTH PATHS ACCELERATE D, F, G
| 42 |  | 197763.7029 | 42000 | 100000 | 152000 | 274881.8514 | 35118.1486 | 14.65%

## 2
Project charter standard outline
as per 2018-PMTermProject_Project_charter_Howto.doc available in course material
What |  | How |  | Weight | Why | Draft Contents
1. | Cover page | 1. | [name of project] | 1 | Provide a conventional ID for future doc management | Cday2019
|  | 2. | Description - Short textual description (max 200 words) in a executive summary format |  | Provide a conventional synopsis for future doc management | organizing the Career Day for graduate students at PoliTo, an event aimed at promoting the job matching between students and companies's recruters
|  | 3. | Approval procedure: |  | Highlight key RACI elements and proedural routing | R = The PM (you) as an internal appointee
A = Servizio Gestione Carriere Studenti
C = Students' bodies and associations, Servizio logistica
I = Delegata del Rettore per gli Alumni e l'Accompagnamento al Lavoro, Vice Rettore per la Didattica, Vice Rettrice per il Trasferimento Tecnologico
2. | Context | 1. | Background - [Why is the project being undertaken?] | 1 | Understand perspective | Increase employability ranking
Promote TT through internships and enterprise thesis
|  | 2. | Goals: |  | Highlight Critical Success Factors | Companies representation > 20
Graduate showoff rate > 20% (=20% * 7000 = 1400)
Employer / students agreements > 20*3 = 60
|  | 3. | Scope |  | Facilitate project planning and benefit realization | finalizing contracts with employers and organizations, setting up on-campus facilities, arrange for refreshments, hire an opening guest speaker, prepare publicity materials and promote the event among students and interested parties.
|  | 4. | Key Stakeholders |  | Facilitate project planning and benefit realization | Students, Companies, Rectorate, PoliTO's administrative departments, Rectorate, Faculty and Departments, Vendors
|  | 5. | Delivery system |  |  | Organizational PM weak matrix, DBB
3. | Metrics | 1. | Key Milestones | 2 |  | Kick off | 2019-01-01
[6 empty] | approval of proj mng plan | 2019-03-25
[6 empty] | finalizing vendor's agreements | 2019-04-08
[6 empty] | pre-occupation review | 2019-04-15
[6 empty] | event (fixed date) | 2019-04-22
|  | 1a. | Duration |  | Start | 2019-01-01
[5 empty] | End | 2019-04-22
[5 empty] | eDays | 111
[5 empty] | wDays | 80
[5 empty] | total work | TBD
|  | 2. | Project Budget |  | Direct costs | Staff = 6*50%* 176 * 1,2 * 55€ = | 34848
[6 empty] | Vendors = 1500/20*3*8*1,2*35€ = | 9450
[5 empty] | OH | 25% of approved DC budget | 11074.5
[6 empty] | Total budget | 55372.5
[6 empty] | say | 55000
|  | 3. | Project Revenues |  | Companies grants | 20*2000€ | 40000
[5 empty] | Internal funds | 1400*15€ | 21000
[6 empty] | Total revenues | 61000
[6 empty] | Margin (pre risk) | 6000
[6 empty] | ROS (or ROC) | 9.836%
4. | CARDS | 1. | Constraints | 2 | Project failure triggers | Fixed date
|  | 2. | Assumptions |  |  | Attendance
|  | 3. | Risks |  |  |  | EMV
[6 empty] | Revenue side = underparticipation p=80% i=20% of revenues | -9760
[6 empty] | Vendors' overcost due to accelerated procurement (p 50%, i=30%) | -1417.5
[6 empty] | Total contingency | -11177.5
[6 empty] | Margin (@risk) | -5177.5
|  | 4. | Dependencies |  |  | Other events in the Career Days programme
|  | 5. | Critical Specifics |  | Organizational assets | Data and documents from previous events
PoliTo's own sources of funding

## 3
Task (AON) | Optimistic duration [weeks] | Most likely | Pessimistic duration | e | d | V | z | p
1-2 | 5 | 11 | 11 | 10 | 1 | 1
1-3 | 10 | 10 | 10 | 10 | 0 | 0
1-4 | 2 | 5 | 8 | 5 | 1 | 1
2-6 | 1 | 7 | 13 | 7 | 2 | 4
3-6 | 4 | 4 | 10 | 5 | 1 | 1
3-7 | 4 | 7 | 16 | 8 | 2 | 4
3-5 | 2 | 2 | 14 | 4 | 2 | 4
4-5 | 0 | 6 | 12 | 6 | 2 | 4
5-7 | 2 | 8 | 14 | 8 | 2 | 4
6-7 | 1 | 4 | 7 | 4 | 1 | 1
[7 empty] | 20 | less than | 23 | more than | less than
1-2-6-7 | P1 |  |  | 21 | 2.4495 | 6 | -0.40825 | 35% | 0.8165 | 21% | 79%
1-3-6-7 | P2 |  |  | 19 | 1.4142 | 2 | 0.70711 | 76% | 2.8284 | 1% | 99%
1-3-7 | P3 |  |  | 18 | 2 | 4 | 1 | 84% | 2.5 | 1% | 99%
1-3-5-7 | P4 |  |  | 22 | 2.8284 | 8 | -0.70711 | 25% | 0.35355 | 36% | 64%
1-4-5-7 | P5 |  |  | 19 | 3 | 9 | 0.33333 | 63% | 1.3333 | 9% | 91%
[7 empty] | P1*P2*P3*P4*P5 | 3.519% |  | 54.91%
CRITICAL PATH ONLY
decision tree
status | outcome | likelihood | utility
S1 | 25 | 25% | 1
S2 | 0 | 39% | 1
S3 | -5 | 36% | 1
average | 4.45 | >0 | positive, bid
MERGE NODE BIAS
decision tree
status | outcome | likelihood | utility
S1 | 25 | 3.519% | 1.5
S2 | 0 | 41.57% | 1
S3 | -5 | 54.91% | 0.2
average | 0.77063 |  | bid