## 1
BCWS | sem 1, 2018 | sem 2, 2018 | sem 1, 2019 | sem 2, 2019 | sem 1, 2020 | sem 2, 2020 | CI | SI($) | EAC (by task)
A ctive substance identification | 170000 | 90000
Preclinical test |  | 50000 | 200000
Clinical test |  |  |  | 280000 | 200000
Commercial launch | [5 empty] | 100000
Marketing support |  | 10000 | 30000 | 50000 | 100000 | 100000
Legal support |  | 20000 | 40000 | 40000 | 20000
Project Management support | 20000 | 20000 | 20000 | 20000 | 20000 | 20000
ACWP | sem 1, 2018 | sem 2, 2018 | sem 1, 2019 | sem 2, 2019 | sem 1, 2020 | sem 2, 2020
A ctive substance identification | 160000 | 110000
Preclinical test |  | 60000 | 220000 | 40000
Clinical test |  |  |  | 232142.86
Commercial launch
Marketing support |  | 10000 | 30000 | 50000
Legal support |  | 20000 | 40000 | 40000
Project Management support | 20000 | 20000 | 20000 | 20000
BCWP | sem 1, 2018 | sem 2, 2018 | sem 1, 2019 | sem 2, 2019 | sem 1, 2020 | sem 2, 2020
A ctive substance identification | 150000 | 110000 |  |  |  |  | 0.96296 | 1 | 270000
Preclinical test |  | 40000 | 180000 | 30000 |  |  | 0.78125 | 1 | 320000
Clinical test |  |  |  | 200000 |  |  | 0.86154 | 0.71429 | 780000.0096
Commercial launch | [8 empty] | 100000
Marketing support |  | 10000 | 30000 | 50000 |  |  | 1 | 1 | 290000
Legal support |  | 20000 | 40000 | 40000 |  |  | 1 | 1 | 120000
Project Management support | 20000 | 20000 | 20000 | 20000 |  |  | 1 | 1 | 120000
TOTAL CUMULATIVE | sem 1, 2018 | sem 2, 2018 | sem 1, 2019 | sem 2, 2019 | sem 1, 2020 | sem 2, 2020
| 1 | 2 | 3 | 4 | 5 | 6
BCWS | 190000 | 190000 | 290000 | 390000 | 340000 | 220000
ACWP | 180000 | 220000 | 310000 | 382142.86
BCWP | 170000 | 200000 | 270000 | 340000
TOTAL CU.MULATIVE
BCWS | 190000 | 380000 | 670000 | 1060000 | 1400000 | 1620000
ACWP | 180000 | 400000 | 710000 | 1092142.86
BCWP | 170000 | 370000 | 640000 | 980000
CI | 0.94444 | 0.925 | 0.90141 | 0.89732
CRITICAL PATH
BCWS | 170000 | 310000 | 510000 | 790000 | 990000 | 1090000
BCWP | 150000 | 300000 | 480000 | 710000
SI($) | 0.88235 | 0.96774 | 0.94118 | 0.89873
SI(t) |  | 0.96429 | 0.95 | 0.92857
CEAC - SOLUTION 1 Acceptable when on critical path . however, not enough taks to consider average behavior
1838171.118 | overhed cost o support are added separately
CEAC - Solution 2 task by task, better method
2000000.0096
Correct to consider that clinical test has a late start. So SI average of preclinical and clinical

## 3
# | Task | Optimitic duration [weeks] | Most likely duration [weeks] | Pessimistic duration [weeks] | Immediate predecessor | e | d | V
A | Basic design | 4 | 5 | 6 |  | 5 | 0.33333 | 0.11111
B | Market analysis | 5 | 6 | 10 |  | 6.5 | 0.83333 | 0.69444
C | Detailed design | 4 | 7 | 10 | Basci design | 7 | 1 | 1
D | Procurement | 9 | 12 | 18 | Basic design; detailed design | 12.5 | 1.5 | 2.25
E | Assembly | 18 | 21 | 27 | Procurement | 21.5 | 1.5 | 2.25
F | Civil works | 24 | 27 | 30 | Procurement | 27 | 1 | 1
G | Testing | 12 | 16 | 20 | Assembly; Civil works | 16 | 1.3333 | 1.7778
H | Setup | 8 | 11 | 14 | Testing | 11 | 1 | 1
I | Advertising campaign | 30 | 50 | 55 | Market analysis | 47.5 | 4.1667 | 17.3611
L | Launch | 6 | 8 | 13 | Setup; Advertising campaign | 8.5 | 1.1667 | 1.3611
[9 empty] | 90 | Z | LESS THAN | MORE THAN
|  |  |  | P1 | A-C-D-E-G-H-L | 81.5 | 3.1225 | 9.75 |  | 2.7222 | 99.68% | 0.3243%
|  |  | CP | P2 | A-C-D-F-G-H-L | 87 | 2.9155 | 8.5 |  | 1.029 | 84.83% | 15.17%
|  |  |  | P3 | B-I-L | 62.5 | 4.4064 | 19.4167 |  | 6.2409 | 100% | 2.176e-08%
[11 empty] | 15.17% | ONLY CP
[11 empty] | 15.45% | MERGE NODE BIAS