## Exercise 1
# | Activity | Predecessor | Duration [months] | Deadline | Risk Profile | Distributed Float (activities)
1 | Concept | - | 6 | September 30th |  | 0
2 | Market study | - | 3 | September 10th | 6 | 2.3333
3 | Engineering | Basic design | 3 | December 31st |  | 0
4 | Prototyping | Engineering | 1 | January 31st |  | 0
5 | Production line installation | Market study | 3 | January 31st | 3 | 1.6667
6 | Production start-up | Prototyping; | 2 | March 31st |  | 0
Prod. line installation
7 | Advertising preparation | Market study | 2 | February 15th | 2 | 2.1389
8 | Advertising campaign | Advertising preparation | 1 | March 31st | 2 | 1.5278
| Paths | Duration | Free Float | Criticality Index | Independent Float (Path)
| 1-3-4-6 | 12 | 0 | 1 | 0
| 2-5-6 | 8 | 4 | 33.33% | 4
| 2-7-8 | 6 | 6 | 0 | 3.6667

## Exercise2
Task name | BAC [k€] | % WS | % WP | ACWP [k€] | BCWP | BCWS | SI per task | orig dur | TEAC
As-is analysis | 20 | 100 | 100 | 24 | 20 | 20 | 1 | 1 | 1
Requirements & needs definition | 100 | 100 | 100 | 90 | 100 | 100 | 1 | 1 | 1
Gap analysis | 40 | 100 | 100 | 30 | 40 | 40 | 1 | 1 | 1
Re-organizational model | 120 | 50 | 20 | 30 | 24 | 60 | 0.4 | 2 | 5
Job definition | 80 | 70 | 90 | 70 | 72 | 56 | 1.2857 | 1.5 | 1.1667
HR assessment | 90 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1
Deployment on pilot department | 30 | 0 | 0 | 0 | 0 | 0 |  | 1 | 1
Full deployment and coaching | 50 | 0 | 0 | 0 | 0 | 0 |  | 1.5 | 1.5
| 530 |  |  | 244 | 256 | 276
Average critical path method | [5 empty] | activity by activity
CI | 1.0492 |  |  |  | CI | 1.0492
SI($) full project (wrong) | 0.92754
SI($) critical path | 0.83636
OPTION 1 - PROJECT DELAYED |  |  |  |  | OPTION 1 - PROJECT DELAYED
CEAC = BAC/CI | 505.1562 | $ |  |  | CEAC = BAC/CI | 505.1562 | full project
TEAC = BC/SI CP | 8.9674 | months |  |  | TEAC = BC/SI CP | 10.5 | or 11 if future tasks with SI=0.84
Price | 709.3845 |  |  |  | Price | 557.6562
Profit | 204.2283 |  |  |  | Profit | 52.5
OPTION 2 - PROJECT BROUGHT BACK ON SCHEDULE better |  |  |  |  | OPTION 2 - PROJECT BROUGHT BACK ON SCHEDULE BETTER
CEAC = BAC/CR | 603.9912 | $ |  |  | CEAC = BAC/CR | 603.9912
TEAC = BC | 8 | months |  |  | TEAC = BC | 8
Price | 903.9912 |  |  |  | Price | 903.9912
Profit | 300 |  |  |  | Profit | 300