## Ex 1.
PROJECT CHARTER
SCOPE OF THE PROJECT | Construction of a cableway facility for ski resort company
GOAL STATEMENT | The project will be build in 25 days with a 4 parallel task (Departure, Arrival, foundation 1 and foundation 2)
RESOURCES | 3 TEAM WORKERS
Budget | Material C | 320000 | TOT | 595000
| OH W/O RESOURCES | 250000
| COST OF LABOUR | 25000
SCHEDULING | the scheduling is made on a project file, you can find in the foulder
SCHEDULING WITH RESOURCES
Solution by student Ferraro

## Ex 2.
Months | PV | EV | AV | ES | Time points | Predictor (time points normalized to PD) | Response (AC-PV normalized to BAC) |  | Project Profile | Values
1 | 370220 | 124120 | 535000 |  | 0 | 0 | 0 |  | Budget at Completion, euro | 21400000
2 | 2080080 | 1333220 | 2461000 | 1.5632 | 1 | 0.14286 | 0.025 |  | Planned Duration, months | 7
3 | 5730920 | 4442640 | 4562480 | 2.6471 | 2 | 0.28571 | 0.115
4 | 9625720 | 7201100 | 7468600 | 3.3775 | 3 | 0.42857 | 0.2132 |  | Actual Duration, months
5 | 16050000 |  |  |  | 4 | 0.57143 | 0.4498 |  | Under/Over budget, %
6 | 19688000 |  |  |  | 5 | 0.71429 | 0.75 |  | Ahead/Behind schedule %
7 | 21400000 |  |  |  | 6 | 0.85714 | 0.92 |  | Actual Time now, month | 4
[5 empty] | 7 | 1 | 1 |  | CPI | 0.96418
[9 empty] | SPI($) | 0.74811
[9 empty] | SPI(t) | 0.84437
[8 empty] | SOL 1) | AC (SPI(T)) | 8.2902 | EAC REVISED | 22194947.9941
[8 empty] | SOL 2) | AC=BC | 7 | EAC(CR) | 29668016.6649
[8 empty] | SOL 3) | AC (SPI($)) | 9.3569 | EAC REVISED | 22194947.9941
[9 empty] | ffp | 29500000
[9 empty] | Penalty per month | 2000000
[8 empty] | SOL 1) | expected price | 26919554.2541
[9 empty] | expected profit | 4724606.2601
[8 empty] | SOL 2) | expected price | 29500000
[9 empty] | expected profit | -168016.6649
[8 empty] | SOL 3) | expected price | 24786181.2779
[9 empty] | expected profit | 2591233.2838

## Ex 3.
Delivery system: BOT
Motivation: major risk is on construction and operations. Contractor better abel to manage these risks. Capex on the contractor
Payment scheme: long term contract payment reimbursed every year to recover initial investment
Financing risk in the contractor
Award: negotiation b/c only few contractors available for this job