## 1
risk: missing as-built drawings means high risk of unknown field conditions and design complexity
better to give design risk to a specialized contractor
Objectives:
highest priority are time (urgent) and quality (to respond to complexity)
non particular focus is on cost
delivery system: DB design-build to give design risk to contractor
payment scheme however should be cost plus to incentive quality, but with time incentive that can be obtained with both cost plus incentive fee (such as 30% share of cost overrun to contractor to avoid delay) plus a time incentive to finish early to mitigate negative effects of pure cost plus fee system
award: negotiation of terms of contact with specialized DB company

## 2
| BAC WS | unit BC | BAC | budgeted duration | Revise BAC | WP | WP | WS | Rev duration | BCWP | ACWP | BCWS | CI | SI
Shaft | 2000 | 65000 | 130000000 | 20 | 130000000 | 1400 | 70% | 65% | 20 | 91000000 |  | 84500000 |  | 1.0769
bottom station | 30000 | 700 | 21000000 | 3 | 21000000 | 0 | 0% | 0% | 3 | 0 |  | 0 |  | TO DO
new station | 20000 | 500 |  |  | 10000000 | 20000 | 100% | 0% | 2 | 10000000 |  | 0 |  | DONE
total |  |  | 151000000 | 23 | 161000000 |  |  |  | 25 | 101000000 | 90000000 |  | 1.1222
CEAC | 143465346.5347 | RAND
TEAC | 21.5714 | months

## 3
Open exercise requiring completeness, accuracy and analysis.
Project Charter
Project Title:
1. General Information:
Sponsoring Organization: |  | Sponsor Representative:
Prepared by: |  | Version:
2. Project Stakeholders:
List all applicable project stakeholders.
Position | Title/Name/Organization | Phone | E-mail
3. Executive Summary
Provide a brief overview of this project.
4. Project Purpose
Explain the reason(s) for doing this project.
4.1. Business Need / Problem
The Business Need / Problem is an issue or opportunity pertaining to the business which needs to be resolved / acted upon. State in specific terms the issue or opportunity this project will address. Often, the Business Need / Problem is a critical business issue or initiative in the Sponsoring Organization’s Strategic Plan.
4.2. Business Objectives
Define the specific Business Objectives of the project that correlate to the strategic initiatives or issues identified in the Sponsoring Organization’s Strategic Plan.
Strategic Plan Element | Project Business Objectives
5. Project Overview
5.1. Project Description
Describe the project focus, approach, customer(s), and the boundary limits of the project.
5.2. Scope
The Project Scope addresses the who, what, where, when, and why of a project.
5.3. Assumptions
Assumptions are statements taken for granted or accepted as true without proof. Assumptions are made in the absence of fact. List and describe the assumptions made in the decision to charter this project.
5.4. Constraints
Constraints are boundary conditions that the project must stay within. List and describe the constraints applicable to this project.
6. Project Requirements / Deliverables
The Project Requirements / Deliverables define what the project must accomplish, including the customer/ user requirements and products / services to be provided by the project.
7. Project Management Milestones and Deliverables
Milestone / Deliverable | Estimated Date | Responsible Individual / Function
8. Costs / Budget
Identify the initial funding required by the project and/or committed to this project by the project sponsor. Additional funding may be requested / committed upon completion of the detailed project plan.
Purpose | Amount | Source
9. Personnel & Other Resources
Resources | Description
10. Project Risks
Risks are statements of issues or problems that have the potential to arise but have not yet occurred. List and describe the initial risks for this project.
11. Project Organization
11.1. Project Organization Chart
11.2. Roles & Responsibilities
Describe the Roles and Responsibilities of all project stakeholders identified for this project (including PESTEL)
Stakeholder Title | Name | Roles & Responsibilities